## Test Plan Overview
LU CRAWLER – FUNCTIONAL TEST PLAN
Resource Sharing Platform ¦ Divyansh Chaurasia ¦ Version 1.0
📋 PROJECT INFORMATION
Project Name | LU Crawler – Resource Sharing System Platform
Prepared By | Divyansh Chaurasia
Date | March 2026
Version | 1.0
Tech Stack | React.js, TailwindCSS, Supabase (Auth, DB, Storage)
Test Approach | Black-Box Functional Testing
Environment | Staging / Local Dev
🎯 SCOPE OF TESTING
IN SCOPE |  | OUT OF SCOPE
✔ User Registration & Login (Supabase Auth) |  | ✘ Performance / Load Testing
✔ File Upload – Notes, Question Papers, Books |  | ✘ Security Penetration Testing
✔ File Download & Preview |  | ✘ Third-party Supabase infrastructure
✔ Search & Filter functionality
🚦 ENTRY & EXIT CRITERIA
ENTRY CRITERIA
• Code deployed to staging environment
• Build is stable (no compilation errors)
• Test cases reviewed and approved
• Test data prepared
EXIT CRITERIA
• 95%+ test cases executed
• All Critical/High bugs resolved
• No open Severity-1 defects
• Test summary report signed off

## Test Cases
LU CRAWLER – FUNCTIONAL TEST CASES
TC ID | Module | Test Case Title | Pre-condition | Test Steps | Expected Result | Actual Result | Status | Priority
TC-001 | Authentication | Valid user registration | User not registered | 1. Open Register page 2. Enter valid name, email, password 3. Click Register | Account created; success message shown; redirected to dashboard | — | Pending | High
TC-002 | Authentication | Registration with existing email | Email already registered | 1. Open Register 2. Enter existing email 3. Submit | Error: 'Email already in use' | — | Pending | High
TC-003 | Authentication | Login with valid credentials | Registered account exists | 1. Go to Login 2. Enter correct email & password 3. Click Login | User logged in; redirected to home/dashboard | — | Pending | High
TC-004 | Authentication | Login with wrong password | Registered account exists | 1. Go to Login 2. Enter correct email, wrong password 3. Submit | Error: 'Invalid credentials' | — | Pending | High
TC-005 | Authentication | Login with unregistered email | None | 1. Go to Login 2. Enter unregistered email 3. Submit | Error message shown; login blocked | — | Pending | Medium
TC-006 | Authentication | Logout functionality | User is logged in | 1. Click Logout button | Session ended; redirected to login page | — | Pending | High
TC-007 | File Upload | Upload valid PDF (notes) | User logged in | 1. Click Upload 2. Select a valid PDF ≤ 10MB 3. Add title/tags 4. Submit | File uploaded; visible in listings | — | Pending | High
TC-008 | File Upload | Upload unsupported file type | User logged in | 1. Click Upload 2. Select .exe file 3. Submit | Error: 'Unsupported file type' | — | Pending | High
TC-009 | File Upload | Upload file exceeding size limit | User logged in | 1. Click Upload 2. Select file > max size 3. Submit | Error: 'File size exceeds limit' | — | Pending | Medium
TC-010 | File Upload | Upload without title | User logged in | 1. Click Upload 2. Select file 3. Leave title empty 4. Submit | Validation error: 'Title is required' | — | Pending | Medium
TC-011 | File Download | Download an uploaded file | File exists in system, user logged in | 1. Search/browse file 2. Click Download | File downloaded successfully | — | Pending | High
TC-012 | File Download | Preview file before download | File exists | 1. Click on file name/preview icon | File preview opens in browser/modal | — | Pending | Medium
TC-013 | Search | Search by exact file title | Files uploaded in system | 1. Type exact title in search bar 2. Press Enter | Matching file appears in results | — | Pending | High
TC-014 | Search | Search with partial keyword | Files uploaded | 1. Type partial keyword 2. Submit search | All relevant files shown | — | Pending | Medium
TC-015 | Search | Search with no matching results | Files uploaded | 1. Search for 'xyzabc123' | 'No results found' message displayed | — | Pending | Medium
TC-016 | Search | Filter by category (Notes/Books/Papers) | Multiple file types uploaded | 1. Select filter: 'Notes' 2. Apply | Only notes category files displayed | — | Pending | Medium
TC-017 | UI/UX | Responsive layout on mobile (375px) | None | 1. Open app in browser 2. Set viewport to 375px width | Layout adjusts; no horizontal scroll; buttons visible | — | Pending | Medium
TC-018 | UI/UX | Responsive layout on tablet (768px) | None | 1. Set viewport to 768px | Layout adapts correctly | — | Pending | Low
TC-019 | UI/UX | Navigation links work correctly | User on home page | 1. Click each nav link (Home, Upload, Browse, Profile) | Each link navigates to correct page | — | Pending | High
TC-020 | UI/UX | Empty state when no files uploaded | New account, no uploads | 1. Login 2. Go to Browse/My Files | 'No files found' placeholder shown | — | Pending | Low
TC-021 | Authentication | Access protected page without login | User not logged in | 1. Directly access /upload URL | Redirected to login page | — | Pending | High
TC-022 | File Upload | Upload duplicate file | Same file already uploaded | 1. Upload file with identical name 2. Submit | Warning shown or file renamed automatically | — | Pending | Low
TC-023 | Search | Search is case-insensitive | File titled 'Physics Notes' exists | 1. Search 'physics notes' (lowercase) | File appears in results | — | Pending | Medium
TC-024 | Authentication | Password field masked | On login/register page | 1. Type in password field | Characters shown as dots/asterisks | — | Pending | Medium
TC-025 | File Upload | Upload multiple files sequentially | User logged in | 1. Upload file 1 2. Upload file 2 3. Upload file 3 | All 3 files uploaded; all visible in browse | — | Pending | Medium

## Bug Report
LU CRAWLER – DEFECT / BUG REPORT LOG
Bug ID | Module | Bug Title | Steps to Reproduce | Expected | Actual | Severity | Status
BUG-001 | Authentication | Login succeeds with empty password | 1. Go to Login 2. Enter email only 3. Click Login | Validation error shown | User logged in without password | Critical | Open
BUG-002 | File Upload | No error on unsupported file upload | 1. Upload a .exe file 2. Submit | Error: 'Unsupported file type' | File accepted silently | High | Open
BUG-003 | Search | Search not case-insensitive | 1. Upload 'Physics Notes' 2. Search 'physics notes' | File appears | No results shown | Medium | Open

## RTM
REQUIREMENT TRACEABILITY MATRIX (RTM)
Req ID | Requirement Description | Module | Linked TC IDs | Coverage | Status
REQ-01 | User shall be able to register with email & password | Authentication | TC-001, TC-002 | ✔ Covered | Covered
REQ-02 | User shall be able to login/logout | Authentication | TC-003, TC-004, TC-005, TC-006 | ✔ Covered | Covered
REQ-03 | Protected pages inaccessible without login | Authentication | TC-021 | ✔ Covered | Covered
REQ-04 | User shall upload files (PDF, DOCX) | File Upload | TC-007, TC-008, TC-009, TC-010, TC-022, TC-025 | ✔ Covered | Covered
REQ-05 | User shall download/preview files | File Download | TC-011, TC-012 | ✔ Covered | Covered
REQ-06 | User shall search & filter files | Search | TC-013, TC-014, TC-015, TC-016, TC-023 | ✔ Covered | Covered
REQ-07 | UI shall be responsive across devices | UI/UX | TC-017, TC-018 | ✔ Covered | Covered
REQ-08 | Navigation shall work correctly | UI/UX | TC-019, TC-020 | ✔ Covered | Covered

## Summary Dashboard
TEST EXECUTION SUMMARY
METRIC | COUNT | NOTES
Total Test Cases | 25
Executed | 0
Passed | 0
Failed | 0
Blocked | 0
Pending | 25
Pass % | 0